## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | MAKE A BENCH PROJECT
PROJECT MANAGER | Matthew Romalis, Melchizedek Ackah-Blay, Becca Godfrey, Richard Zhou
COMPANY NAME | Team 2 0301
DATE | 2024-02-29 | [5 empty] | Bench Strucuture and Design | [14 empty] | Material Gathering | [14 empty] | Assembling the Bench | [14 empty] | Testing and Selling the Bench
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
[7 empty] | 2024-03-04 |  |  |  |  | 2024-03-11 |  |  |  |  | 2024-03-18 |  |  |  |  | 2024-03-25 |  |  |  |  | 2024-04-01
| Developing blueprint for the bench | Matt, Mel | 2024-03-04 | 2024-03-11 | 5 Days | 0%
| Shopping for the best wood, metals etc | Mel, Matt, Becca, Richard | 2024-03-05 | 2024-03-07 | 2 Days | 0%
| Figuring out dimensions for our bench materials | Becca, Richard | 2024-03-05 | 2024-03-14 | 8 days | 0%
| Coming up with multiple bench prototypes | Mel | 2024-03-05 | 2024-03-14 | 5 Days | 0%
| Aligning pieces and making sure they fit | Richard | 2024-03-05 | 2024-03-14 | 5 Days | 0%
| Building the bench using our final materials | Mel, Becca | 2024-03-15 | 2024-03-20 | 4 Days | 0%
| Painting the bench | Matt | 2024-03-21 | 2024-03-22 | 2 Day | 0%
| Applyign the second paint coat | Mel | 2024-03-25 | 2024-03-25 | 1 Day | 0%
| Reviewing the bench | Mel, Matt, Becca, Richard | 2024-03-26 | 2024-03-28 | 3 Days | 0%
| Team members individually test the bench | All team members | 2024-03-29 | 2024-03-30 | 2 Days | 0%
| Do a series of test: water, rain, sand, hit test | Richard | 2024-04-01 | 2024-04-03 | 3 Days | 0%
| Put the product on various online stores | Becca | 2024-04-03 | 2024-04-04 | 2 Days | 0%
| Deliver the product to the customer | Mel | 2024-04-05 | 2024-04-06 | 2 Days | 0%
0%
0%
0%
0%
0%
0%
0%